## Sheet1
Surface Water Quality Assurance Project Plan (QAPP) Checklist
Description |  | Page/Section
Project Management
1 | Title Page
2 | Distribution list
3 | Table of contents
4 | Project/Task organization – identify key project team members and their respective roles and responsibilities (facility manager, operator, environmental project manager, hydrogeologist, field sampler, chemist, statistician, etc.). This may be provided in a table format
Problem Formulation/Background
5 | State purpose of plan, decisions to be made, or outcome to be achieved
6 | Background information - historical, scientific, and regulatory perspective for the monitoring project including:
a. Facility location, local surface hydrology, geology and hydrogeology, and monitoring program history and current status
b. Identify all monitoring locations and current status (active or inactive, etc.)
c. Constituents monitored for and, as applicable, explain why any 40 CFR 258 Subpart G Appendix I or Appendix II constituents or 18 AAC 60 Table F constituents have been removed from the list, and attach ADEC approval letter
7 | Applicable regulation or program – specific quality standards, criteria, or objectives
a. Type of monitoring and applicable regulations
b. Compliance criteria - Solid Waste Program Surface Water Standards Table
Project/Task Description
8 | Facility map with monitoring locations and predominant surface water flow direction and grading information
9 | Monitoring schedule information
a. Frequency of scheduled monitoring events
b. Timing of scheduled monitoring events (or an acceptable range)
Data Quality Objectives and Criteria
10 | State all data quality objectives (DQOs) and specify performance criteria
a. Include a list of all monitoring locations to be sampled during each monitoring event
11 | Indicate how non-conformance issues will be identified and documented, and the process for determining corrective actions
Special Training/Certification
12 | Identify any specialized training or certifications required and provide documentation of that training for project team members
Documents and Records
13 | Describe and identify all documents that will be produced under QAPP, the format for those documents, how they will be distributed, and the document retention policy
Data Generation and Acquisition
14 | Sampling information
a. Sample identification
b. Number of samples
c. Sampling rationale
Sampling procedures
15 | Sample collection equipment
a. Type of equipment used for sample collection
b. Certified pre-cleaned sample containers
c. Other consumables (Personal Protective Equipment, etc.)
16 | Sample preservation and hold time (See DEC Contaminated Sites: Field Sampling Guidance)
17 | Decontamination and disposal procedures (including field parameter screening equipment)
a. Use of disposable equipment
b. Decontamination of reusable equipment
Field Sampling Performance Standards
18 | Instrument checks and calibration procedures
19 | Identify how non-conformance issues will be identified and documented, and the process for determining corrective action
Sample Handling and Chain of Custody (COC) Procedures
Describe how COC will be maintained from sample collection through delivery to the lab (Note: Labs must maintain COC if they transfer samples to another lab.)
20 | How field procedures will be documented
a. Field log
b. Monitoring sampling forms
c. COC form
21 | Sampler credential requirements
22 | Sample collection and management in the field (sample storage, etc.)
23 | Sample transport to lab (hand delivered, Gold Streak, etc.)
Analytical Methods
24 | Analytical lab and applicable certifications or approvals
25 | Analytical methods (Method name and SW-846 method number)
26 | Detection and quantitation limits for all monitored constituents (Detection Limit, Limit of Detection, and Limit of Quantification must be provided by laboratory, refer to Department of Defense (DoD) fact sheet for definitions)
27 | Confirmation of analytical detection limit adequacy to meet monitoring program objectives (prior to analysis)
28 | Confirmation of laboratory adequacy for analytical limit reporting requirements (prior to analysis). Refer to DoD factsheet for reporting requirements.
29 | Analytical turn-around time (TAT) – standard TAT is 30 days
30 | Identify who will manage lab contract to ensure all lab analyses are done in accordance with QAPP
Quality Control (QC)
31 | Field equipment use, maintenance, and verification – including manufacturer manual, instrument calibration and frequency, use, decontamination, calibration verification
32 | Field QC samples
a. Field duplicates – identify procedures and frequency (1 per 10 samples or at least 1 per sampling event)
b. Trip blank – must be submitted with all volatiles samples [gasoline-range organics (GRO), volatile organic compounds (VOC), ethylene dibromide (EDB), etc.]
c. Temperature blank – must be included in each sample cooler
33 | Laboratory QC Samples
a. Method blanks
b. Lab duplicates
c. Lab control spike/duplicates
d. Matrix spikes/duplicates
e. Surrogate Spikes
34 | Data Quality Objective Evaluations
a. Accuracy
b. Precision
c. Completeness
d. Sensitivity
e. Comparability
f. Representativeness
35 | Data assessment - describe how data will be assessed for usability
a. Data reduction – what result will be used (See CS Tech Memo Treatment of Non-Detect Values, Data Reduction for Multiple Detections and Comparison of Quantitation Limits to Cleanup Values)
i. Field duplicates – use most conservative (highest for compliance; lowest for background)
ii. Results from multiple analyses – use more definitive method or most conservative result
b. Comparison to DQOs – detection limit adequacy, compliance with QA/QC criteria
c. Guidelines for identifying and handling non-conformances (what to do when things go wrong)
d. Corrective actions (reanalysis, reporting data with qualifications, resampling, etc.)
e. Data qualifications
i. How data will be qualified (flagged) – provide reference to EPA’s National Functional Guidelines or other guidance
ii. Define data flags to be used
iii. Impact on data usability – biased high or low or rejected (cannot be used at all)
Data Management
Describe how data will be managed from generation to final reporting
36 | Record keeping
37 | Data storage and retrieval – all historical monitoring data should be available
38 | Data handling
39 | Programs/software used to process, compile, and analyze data (Access, Excel, etc.)
Statistical Approach - Identify the following:
40 | Statistical approach
41 | Error levels
42 | Distribution testing
43 | Data reduction for statistical analysis
a. Duplicate data – use more conservative result (highest for compliance; lowest for background)
b. Non-detects
i. Kaplan-Meier or bootstrap method recommended where sufficient data available (depends on percentage of NDs)
ii. Highest ND detection limit if not enough data
iii. Analytical limit used for non-detect results
c. All qualified data – should be used as is (discuss any potential bias as an uncertainty). Rejected data should not be used at all
d. Statistical outliers – include background testing procedures and evaluation criteria for eliminating any data point; outliers may only be eliminated in background analysis unless field or lab error can be confirmed
e. Trend analysis – include method and whether or not the analyses are used to look for trends over time or if it is used to look at seasonal variability
Reporting
44 | Reporting schedule – frequency of reporting (quarterly, semi-annual, annual) and when reports will be submitted (within 90 days of sampling event)
45 | Retesting and resampling reporting schedule (if applicable)
46 | Report format – electronic draft, red-line strike-out review, final hardcopy with CD, etc.
47 | Review process
a. Who develops reports?
b. Who reviews them?
c. Review schedule
d. Reconciliation of comments and final approval